## Slide 1: ATS
ISO27001 – SLT Summary and Review
November 2024

## Slide 2: Introduction & Contents
  Introduction
  Executive Summary
Project Exec Summary & Actions
Scope
ISO27001 - GAPs
Next Steps
Appendix
  Previous exec summaries
Name | Title | Contact | Attendees
# | Decision | Owner | Status | Update Due
Decision log

## Slide 3
ISO27001 – Project Requirements and Milestone Summary
Org Context & Build ISMS
Finalise core ISMS, Risk Management Framework Supplier selection, Information Security Policy, Project Plan and Statement of Applicability.
29th Feb –
31st March 24
Project Team & Resource Requirements
Service Owners – 0.2 Weekly
Infrastructure – 0.2 Weekly
PM – 0.2 Weekly
Security – 0.5 Weekly
Management – 0.1 Monthly
Enablers
ISO 27001 Training
Trustwave consultancy / KCM / Teams Project Tracking
Implement Management System & Controls
Resolve any outstanding control gaps. Develop Operating procedures, implement the controls defined, Train ATS and measure performance
Conduct Pre-Audit with Trustwave
3rd June –
31st July 24
Early-Stage Audit – Targeting end of Aug for Audit
Complete review of all implementation and documentation with external Auditor.
Revise any deviations for Q4 External Audit
1st Aug –
1st Oct 24
External Audit & Accreditation
Conduct external audit after reviewing with Trustwave
2nd Oct 24 -
31st Dec
Pre-Audit and GAP Analysis
Conduct GAP Analysis, identify & treat Risks, setup governance forums, Leadership review & select auditor.
1st April –
31st May 24
Project Kick off / Initial Scoping / Strategy
Define Project Structure, ISO27001 Training, Scope, Design the Information Security Management System
31st Jan -
28th Feb 24
Executive Summary
ISO27001 is a globally recognised framework, containing guidance on establishing / maintaining an Information Security Management System (ISMS). Aggreko aim to become certified to support our customers and win new business. To achieve this, we will use the Plan Do Check Act Model to build the ISMS (Themes 4-10) and meeting the Appendix A (93) controls.
This presentation details the approach Aggreko will take to accomplish this.
Organisational Scoping & Rationale
Focus on the customer facing systems or any systems with secure / confidential information. Assets include information. This is based on legal, contractual obligations, Business Requirements and Risk Assessment.
ATS – Glasgow GTC
Infrastructure / Cloud Services & Networks – Service related
Internal only services: Cloudsuite, SalesForce, Aggreko Connect, ARM and Sitewatch.
Delivery Options
Consultant – Scope, build, manages & implements ISO27001
Hybrid – ATS managed with consultancy
Internal – All internally managed by ATS.
Recommended Hybrid – Cost effective and supports control.
Key Risks and Issues
Resourcing – Intensive for all teams to contribute to the policies and prove compliance.
Knowledge – ISO training required for teams
Controls – Data Masking, Business continuity, disaster recovery and SIAM.
Management – Agree Leadership buy in through governance structure, risk management and performance
Approval Committee & Structure
Weekly Project Meetings – Project Summary Report
Monthly Steer Co – Summary management report
Milestone Stage Report – Detailed progress report for each stage 1-6
Immediate next steps
Accept risks / Conduct GAP analysis
Leadership buy in
Agree Check Points
Agree project structure
Agree training
Sign off Scope / SOA with Management agreement – post Trustwave discussion.
2
3
4
5
6
1
Note: Timelines and resourcing are subject to change, until scoping and gap analysis are complete.
Milestones
Targets

## Slide 4
ISO27001 – Executive Summary
ISO27001 Flash Report |  |  |  |  |  |  |  |  |  |  | 
Programme Governance: |  | Denis Gallacher / Connor McCann |  |  | Budget Status: |  |  | Budget Status: | Unknown |  | 
Status Date: |  | 01/11/24 |  |  |  |  |  |  |  |  | 
Overall Status |  | Green |  |  |  |  |  |  |  |  | 
Target end date: |  | 31/12/24 |  |  |  |  |  |  |  |  | 
Programme Stage: |  | Delivery |  |  |  |  |  |  |  |  | 
Executive Summary |  | We have passed the first stage audit, but the risk management framework is the priority for the 11th November |  |  |  |  |  |  |  |  | 
Challenges / Concerns: |  | Resourcing and timelines |  |  |  |  |  |  |  |  | 
# |  | Action |  | Update | Owner | Owner |  | Due |  | Status | Status
32 |  | Complete the detailed audit schedule with all information required by teams |  | 01/11 – Full end to end schedule complete, require the SLT to review. | DG / CM | DG |  | 01/11 |  | Closed | In progress
33 |  | Complete action plan for SLT and the project |  | 01/11 – An action plan for both the SLT and Project to resolve outstanding issues (see next slides) | DG / CM | DG |  | 01/11 |  | Closed | In progress
34 |  | Complete team briefing sessions |  | 01/11 – These have been scheduled for the November audit |  | DG |  | 01/11 |  | Closed | 
35 |  | Resolve risk management major non conformance |  | 01/11 – The auditor reported that the process is poor and doesn’t include opportunities. We are reworking the entire risk framework as well as closing historical risks. We will need to demonstrate audit plans. |  | DG |  | 08/11 |  | In progress | 
36 |  | Rework the risk SharePoint to include opportunities, non- conformance register and security CSI |  | 01/11 – We need to rework the SharePoint to be a central point for all requirements of the ISMS including: Corporate Risk, Operational Risk, Non-Conformance and CSI. |  | DG |  | 08/11 |  | In progress | 
37 |  | Resolve any outstanding control GAPs |  | 01/11 – There are approx. 15 controls that need revised, which have bene included in the detailed audit schedule. The outstanding control GAPS need to be resolved. If evidence is unavailable, then the teams should comment what they will discuss. | DG | SH |  | 28/11 |  | In progress | In progress
Key Issues and Challenges |  |  |  |  |  |  |  |  |  |  | 
# | Description | Description | Update |  |  | Type (RAID) | Type (RAID) | Type (Risk / Issue/ Defect) |  |  | Status
R1 | Resource |  | 01/11 – Stretch targets are being met, but contingency on approvals for control standards. |  |  | Risk | Risk |  |  |  | Open
R2 | Data Masking, Business continuity, disaster recovery and SIAM. |  | 01/11 – DG creating a control standard and agree mitigation for any BCP planning. |  |  | Risk | Risk |  |  |  | Open
R3 | ISO has to be operating 3 months before audit |  | 01/11 – Data sets and historical evidence available but requires alignment with measurement and analysis clause. |  |  | Risk | Risk |  |  |  | Open
R4 | Document volume |  | 01/11 – Management clauses in final draft, require completion of control standards. |  |  | Issue | Issue |  |  |  | Open
Key | Closed | In progress | Issue

## Slide 5
SLT Actions
ISO27001 - Certificate Action Plan (SLT) |  |  |  |  |  |  |  |  |  | 
Item | Description | Description | Priority | Critical path? | Owner | Comments | Support Required? | Status | Due Date | Attachments
ISO Stage 2 - Management Review |  |  |  |  |  |  |  |  |  | 
1 | Issue comms for security policy | Request CIO send policy / link with the ISMS SharePoint for evidence. Sample email provided. | High | Y | GN / DG | Release comms - Supports awareness and communications evidence | GN | Open | 08/11/2024 | 
2 | CIO Job Description | Agree job description to support ISO | High | Y | GN | Completed and uploaded | GN | Closed | 06/11/2024 | 
3 | Agree off signage | Provide a draft for digital signage and put in the office space | High | Y | GN / DG | AH has released to the office boards | EUC | Closed | 06/11/2024 | 
4 | Review Management Report | Provide feedback on the overall management report and put into template | High | Y | SLT | This is part of the 11th November Audit | SLT to review and provide output, we will put this feedback into a 'meeting minutes format' | Open | 06/11/2024 | 
5 | Management report meeting minutes | Complete a meetings minute format and input SLT output | High | Y | DG | N/A | SLT | Closed | 06/11/2024 | MGT Template
6 | Revise risk management | End-end review and modification of risk management with Trustwave support | High | Y | DG / DJ | Revise the risk plan. Attending Cannock 4th & 5th November to complete | Trustwave Approval - RC / DJ | Open | 08/11/2024 | 
7 | Review new risk management framework | Send the new risk management framework and updated clauses to SLT | High | Y | DG | Send to SLT once complete - condensed schedule | SLT | Open | 06/11/2024 | 
8 | Close historical risks - prior to 2022 | Close or transfer any historical risks. Reopen as 2024 for remaining. | High | Y | DG | Making excellent progress | SLT | Open | 08/11/2024 | 
9 | Revise Risk reporting & SP | Update entire SP with risks and present to the SLT | High | Y | DG | In progress, MH support rework. | N/A | Open | 08/11/2024 | 
10 | Support treatment plans for risks | Develop risk treatment plans | High | Y | SH | Follow up post risk reviews with Trustwave | All teams | Open | 08/11/2024 | 
11 | Review resources for audit | Confirm from the plan resource availability | High | Y | SLT | Only requires confirmation and can be closed | SLT | Open | 08/11/2024 | Audit schedule
12 | Legislation subscriptions | We need to prove were updating the ISMS based on legal and regs | High | Y | DJ | No systems exists, but Trustwave have provided an approach | DJ | Open | 08/11/2024 | 
13 | Contact with external authorities and comms | Meeting setup to agree and review process with AW / GN. DG Creating processes | High | Y | DG | Trustwave recommend putting into Cyber procedure. | AW / GN | Open | 08/11/2024 | 
14 | Corporate risk register & opportunities | Reworking the SP to build opportunities and org risks using Ian's framework | High | Y | DG | Agree with GN / DJ if these are accurate representations | GN / DJ | Open | 08/11/2024 | 
15 | Sales, Marketing and Finance Support | Review with auditor on the 1st Nov to confirm what is required here. | High | Y | DJ / DG | Segregation of duties - consultants & Aggreko ISO leads have never heard of this. | Auditor / Trustwave | Open | 08/11/2024 | 
16 | Support Annex A Control resolution | We have all controls complete for the Nov audits, follow up on Dec. | Medium | Y | SH | SH to follow up with team leaders | Team Leaders / SLT | Open | 04/12/2024 | 
17 | Vulnerability Management | Continue supporting vulnerability reduction. | High | Y | AN | 3-month trend minimum required in Service Ops report. Discuss at SecOps forum. We will not fail on this basis. | AN - potentially attend control review | Monitor | N/A | 

## Slide 6
SLT Actions
ISO27001 - Certificate Action Plan |  |  |  |  |  |  |  |  | 
Item | Description | Stage 2 Critical Path | Priority | Owner | Comments | Support Required? | Status | Due Date | Attachements
1 | Revise Risk Management Framework | Y | High | DG | Cannock visit and output | Trustwave | Open | 08/11/2024 | 
2 | Control and assurance check of management review and controls for stage 2 Nov audit | Y | High | DG / SH | DG check management clauses / SH review controls | SH | Open | 08/11/2024 | 
3 | Create NCR / CSI / Opportunities register on SP | Y | High | DG / MH | Discuss with Murron for support | MH | Open | 08/11/2024 | 
4 | Revise SP for Risk Management based on framework outputs | Y | High | MH | DG work with MH on new fields | MH | Open | 08/11/2024 | 
5 | Update management clauses with non-conformances and interested parties | Y | High | DG | Already exists - use SWOT & PESTEL Updated Internal Audit with categories, Management Review and Interested parties Trustwave updates required to close | N/A | Open | 08/11/2024 | 
6 | Revise planning section with more on risks | Y | High | DG | Complete when framework is reviewed | N/A | Open | 08/11/2024 | 
7 | Complete Management Review meeting minutes template | Y | High | DG | Awaiting output from SLT review 31/10 - Review minutes template complete | SLT | Closed | 08/11/2024 | 
8 | Ensure Service Ops reports are complete for Nov | Y | High | SH | Follow up with Rob / John | EIS | Open | 08/11/2024 | 
9 | Follow up with minor nonconformities and correct | Y | High | DG | LRQA report and Trustwave feedback | N/A | Open | 08/11/2024 | 
10 | Schedule meetings with all the teams for the Stage 2 Audit | Y | High | DG | Awaiting schedule agreement | SLT | Open | 08/11/2024 | 
11 | Schedule breifing meetings with all the teams prior to their Stage 2 days | Y | High | DG | Awaiting schedule agreement | SLT | Open | 08/11/2024 | 
12 | Version control checks on all documents and version upgrade check on documented information | Y | High | SH | Review the management clauses and evidence for versions. Should be at least V1 | N/A | Open | 08/11/2024 | 
14 | Follow up on Annex A Controls for Dec | Y | Medium | SH | Follow up with the teams on the control evidence prior to Dec Audits | Team Leaders | Open | 08/11/2024 | 
15 | Proof of legislation and reg changes - automated system | Y | High | DG | Meetings arranged with Vendors | DJ | Open | 08/11/2024 | 
16 | Communications planning for Cyber Incidents | Y | High | DG | Working with Grant / Annette to resolve | GN / AW | Open | 08/11/2024 | 
17 | Version control checks on all documents and version upgrade check on documented information | Y | High | SH | Review the management clauses and evidence for versions. Should be at least V1 | N/A | Open | 08/11/2024 | 
18 | Review statement of applicability and bring to version V4 | Y | High | SH | Revisions should be consistent | N/A | Open | 08/11/2024 | 
19 | Arrange governance meetings | Y | High | DG | Speak to Rob re Vulnerabilitiy / Asset and Risks | All Teams | Open | 08/11/2024 | 
13 | Arrange Team ISO drop in sessions | Y | High | DG | Agreed with GN | N/A | Open | 04/12/2024 | 

## Slide 7
Internal and External issues
Category | Internal Issues | External Issues
Organizational Structure | - Hierarchical structure and reporting lines - Roles and responsibilities within the organization | - Regulatory environment - Compliance requirements and legal obligations
Governance | - Policies, procedures, and standards - Internal audits and compliance mechanisms | - Industry trends and market dynamics - Competitive landscape and pressures
Resources | - Availability of skilled personnel - Financial resources and budget allocations - Technological resources and infrastructure | - Emerging technologies and their potential impact - Threat landscape and evolving cyber threats
Processes | - Core business processes and their alignment with security objectives - Information handling and data management practices | - Security practices of suppliers and third parties - Dependencies on external service providers
Culture | - Organizational culture and employee awareness of information security - Commitment of leadership to information security | - Public perception and trust in the organization - social media and public communication channels
Past Incidents | - History of security breaches or incidents - Lessons learned from previous security events | - Natural disasters and environmental risks - Physical security of facilities and data centres
Capabilities | - Technical capabilities and expertise - Capacity for response and recovery in case of incidents | - Political stability and government policies - International relations and geopolitical risks
Economic Factors | - Economic stability and financial health of the region - Global economic trends affecting the organization | - Economic stability and financial health of the region - Global economic trends affecting the organization
Risks and Opportunities can be derived from the below issues, is there anything we should add?

## Slide 8
Opportunities Management
As part of the Risk and Opportunities clause we need to identify opportunities for improvement. An example opportunities register has been created, and the type of opportunities are detailed below (see appendix for further examples)
Market trends and industry best practice – Industry forms, conferences and benchmarking with competitors.
Internal and external audits – addressing nonconformities, implementing recommendations from management reviews and objective setting based on audits.
Customer requirements – Evolving customer security measures, developing new security features and achieving certs for customer contracts.
Mergers and Acquisitions – Enhancements and complimentary systems, processes, people and technology to improve information security.
Risk: Refers to the potential for loss or harm related to information security. It is typically defined as the combination of the likelihood of an event occurring and its impact. Proactively identifying and managing risks to prevent negative outcomes.
Opportunity: The potential for improvement or beneficial outcomes related to information security. Opportunities can arise from various sources and can help in enhancing the ISMS, achieving better compliance, and fostering a culture of continuous improvement. Recognizing and acting on opportunities to achieve positive outcomes and continual improvement.

## Slide 9
Risk Management update
Corporate Risks
Ian’s Framework
Tag on Ops risks to link
Separate register
What opportunities are available e.g. Infosec resource – risk but op to improve
Links external and internal issues
Operational Risks
Detail ISO Risks & other control frameworks / separate register
Streamline
Treatment plans
Direct link to corporate risks
Links external and internal issues
Revised tolerance – critical goes to corporate
We are making excellent progress with the Risk Management closure from 2022:
There are 106 historical risks and 38 have been closed.
There is good justification to back up all closures.
All teams are continuing to update the risk registers.
Revised Risk Framework
Link Opportunities
Link Opportunities
We are not ISO27005 accredited and do not plan to be, therefore Risk Management becomes similar, but we will broadly align to those principles. Below is a possible revision to the Risk Management framework and we will be looking to align this with the current documentation. Trustwave working on new framework.

## Slide 10
ISO27001 – Go to Green Plan for Stage 2
Description | Issue / Risk | Corrective Action | Date | Owner | Impact | Status
Complete an internal audit | We must complete an internal audit for to demonstrate awareness and correction to non-conformities. | We completed the internal audit on the 11th September. Corrective actions will be added to this plan, when the report is available. | 11/09 | DG / CZ / DJ | Major / High | Closed
Scope modifications | Scope is insufficient according to LQAR. | Add information to confirm what ‘Aggreko’ does as a business. SLT to sign off. | 30/09 | DG | Major / High | Closed
Management Clauses | GAP Analysis identified minor corrections, including scope needing to be expanded and Information Security objectives to be moved to SMART. Evidence must be produced from the management meetings. | Correct management clauses and the SLT must have reviewed and signed off by the end of the month. | 30/09 | DG / CZ / SH | Major / High | Closed
Annex A: Evidence Gathering / Controls Assurance | Internal audit indicated that evidence was insufficient for a multitude of controls. Some teams have detailed evidence where others have not. | All evidence must be uploaded by the end of September. Meetings with all parties scheduled to clearly state the evidence required and a follow up email with the details. | 30/09 | Infra / Service Owners | Major / High | Closed
Security Monthly Service Reporting | This has been requested to complete the monthly Service Operations report. This has not been complete, impacting our evidence and management control reviews to demonstrate trends. | Meetings have been setup with a team, with a requested draft to be completed by the 18th September to be added to the 11th October Service Operation Forums to demonstrate reviews prior to audit. | 30/09 | EIS / EUC / | Major / High | Closed
Vulnerability Management | Due to changes in technology additional vulnerabilities have been detected, these have started to be reduced but are not trending down to a sufficient level. | Resolve vulnerabilities. We need to demonstrate a downward trend or several remediations as per our vulnerability policy and / or standard. | 30/09 | EIS / CZ | Major / High | Monitor
Governance Boards & Management Review | All governance boards must be setup with meeting minutes complete. Create Management and finalise management report. | Arrange Asset, Management & Risk Reviews and ensure that all meeting minutes are available for the auditor. Risk reviews are now setup as well as Darren’s update to the exec. | 30/09 | DJ / DG | Major / High | Closed
Project Management & Data Training / Evidence | Incomplete, needs to be completed to advise of controls and standards that need to be met. | Complete the training and ensure that the Project Managers are following processes. We need evidence to demonstrate risk management and adherence to change / service requirement management. | 30/09 | CZ | Medium / Minor | Closed
Non-Compliance Reporting | All teams have not uploaded their non-compliances against the standards that have been provided. We are awaiting feedback, but if the auditor finds any that have not been raised this is an automatic failure. | Contact all service owners to set a new deadline of the 30th September 2024. Completed review and added to the document control list. Added non compliances. Reviewed policies and standards to add what was required and map to controls, raise noncompliance e.g. data classification user encryption guide. | 30/09 | CZ / Infra / Service Owners | Major / High | Closed
Conduct a full end-end review | We need to ensure everything required for the auditor is available and we are fully transparent with any non-conformities or serious risks. This will allow us to explain issues rather than experiencing a failure. | Conduct an end-end analysis of all evidence and documentation to ensure completion and readiness for audit. | 14/10 | DG / CZ | Major / High | Closed
Resource identification for Audit | We need to ensure that resources are available over the audit dates and periods. | Discussion with the Team Leaders to identify a key resource to support on dates they are not available. | 30/09 | DG | Major / High | Closed
Impact | Impact / Description
High / Major | Will result in ISO Failure
Medium / Minor | Will be reported as a risk / issue or non-conformity.
Low | No impact to ISO achievement, but nice to have.
Note: Once we receive the internal audit feedback, we will update this plan.

## Slide 11
Questions and Answers

## Slide 12
ISO27001 - GAPs
GAP / Concern | Description | Possible Mitigation | ISO27001 Achievement Comments | Impact
Audit and Compliance | We have created the ISO Management Clauses / Controls and Service Management Global IT Policies. Any internal audit is Self-Governance. | Discussion with our Audit Team / Leads to understand if they could run an internal audit. Discuss how HSE have approached this. | This could have an impact or cause ISO to fail without independence from the Management and Control owners | High
Vulnerability Management | We need to improve the Vulnerability Management process as they have increased to 250K | Follow up on high level review and enforce governance meetings with tracking. | This could impact our certification based on the standards. | High
Data and 3rd party Standard | There is an issue with legal and the wording of both policies. This was previously on the Global Hub but was advised this hasn’t been approved. | Meeting with legal on the Wednesday the 7th to review. Focus on ATS Scope | This could impact the overall ISO audit as data classification standards are key part of the Information System. | High
Information Mapping | Information assets data mapping and understanding were this is located. | High Level Review | This is expected from the ISO audit as it is part of our scooping. Requirement of framework. | High
Not a dedicated Incident Responder Team and no one is officially certified. | As part of best practice, we would have a team or specific employees who would focus on running the end-end of a Security Incident Management. We find that we have continuously refresh training for contacting our suppliers e.g. Trustwave. Currently best efforts. | Possible training for individuals to become incident responders, but this would need to be Global or a dedicated head. | Will not fail ISO but would require agreement on structure and learning. May be listed as a non-conformance and external contacts. We need to evidence and have records but need resource to support this. | Medium
No dedicated Security Information system | Ivanti / ITSM is not fully configured designed for security incidents | Working with Jude to identify if we can segregate like HR was. | Ideally, we would want all records within Ivanti, this could be listed as a non-conformance, but not a failure. | Medium
Information Security Systems / Metrics | Our systems and metrics are not all within one system, which affects record tracking and causes duplication of effort. | Review all systems and understand where we can combine and create a dashboard e.g. PowerBI | Will not fail ISO, but there will be an expectation around data sets being centralised within one location for easy report. | Medium
GTC Security Signage | We currently have no type of signage for the security standards. | We will create some leaflets in the GTC with Security Best practice and access to the Comms Room at the Sentinel site. | This is part of the awareness clause. This is not an issue to address. | Low
Impact | Impact / Description
High | Possible failure impact for ISO.
Medium | Will be reported as a risk / issue or non-conformity.
Low | Minor impact but needs to be resolved.

## Slide 13
ISO27001 – Revised Scope
Original Scope of the Information Security Management System
“Information security and data assets supported and managed by the Glasgow ATS team, for our critical business applications
Revised Scope of the Information Security Management System
“Information security and data assets supported and managed by the Glasgow ATS team, for our critical business applications, to ensure the secure provision of mobile modular power, temperature control and energy solutions”
Example ISO27001 Certification
This is to certify that Aggreko holds certificate no XXXXX, and operates an Information Management System which complies with the requirements of ISO/IEC 27001:2022 for the following scope
“Information security and data assets supported and managed by the Glasgow ATS team, for our critical business applications, to ensure the secure provision of mobile modular power, temperature control and energy solutions”
The overall scope for the ISO27001 Information Security Management has been requested to be updated with LRQA:

## Slide 14
Appendix

## Slide 15
Next Steps to Certification
Ongoing
Risk – identification, assessment, ownership and treatment (ongoing)
Mid-August
Information Asset Mapping.
Controls Assurance (Reporting).
Complete final training – Management, Data Standard and 3rd Party.
ISMS Manual finalisation – Governance / Overall Policy Statement.
Audit agreement
End August
Global Standards and policies are uploaded comms plan – Finalise on the ISMS SharePoint.
Data and 3rd Party Standard

## Slide 16
Decision Log & Project Change Control
# | Description | Owner | Status | Due
1 | ISO27001 – Training | DG | Approved / Closed | 07/03/24
Change Summary | Description | Approved by | Solution design updated?
Change control log
Decision log

## Slide 17
ISO27001 – Executive Summary
ISO27001 Flash Report |  |  |  |  |  |  |  |  |  |  | 
Programme Governance: |  | Denis Gallacher / Connor McCann |  |  | Budget Status: |  |  | Budget Status: | Unknown |  | 
Status Date: |  | 01/11/24 |  |  |  |  |  |  |  |  | 
Overall Status |  | Green |  |  |  |  |  |  |  |  | 
Target end date: |  | 31/12/24 |  |  |  |  |  |  |  |  | 
Programme Stage: |  | Delivery |  |  |  |  |  |  |  |  | 
Executive Summary |  | We have completed and internal audit, control gaps must be resolved. |  |  |  |  |  |  |  |  | 
Challenges / Concerns: |  | Resourcing and timelines |  |  |  |  |  |  |  |  | 
# |  | Action |  | Update | Owner | Owner |  | Due |  | Status | Status
18 |  | Complete mandatory control documentation & finalise performance |  | 13/09 – Awaiting completion of the 3rd party standard. | DG / CM | DG / CM |  | 30/09 |  | In progress | In progress
20 |  | Training Plan and Develop Operating Procedures. |  | 13/09 – Project Management training to be completed. | DG / CM | CM / CZ |  | 30/09 |  | In progress | In progress
21 |  | Setup governance forums & begin risk treatment reviews |  | 13/09 – Governance forums have been setup; management reporting needs to be completed. | DG | CZ |  | 30/09 |  | In progress | In progress
19 |  | Finalise Management clauses & SLT review |  | 13/09 – Updated Management Clauses based on GAPs and resubmit for review. |  | SLT |  | 30/09 |  | In progress | 
26 |  | Information asset mapping |  | 13/09 – complete information asset mapping for our key systems e.g. PII etc. Affected by Data Standard. |  | DG / SO’s |  | 30/09 |  | In progress | 
27 |  | Create a go to green plan |  | 13/09 – Create a go to green plan to address all challenges prior to audit. |  | DG |  | 13/09 |  | Complete | 
28 |  | Reviews with Services Owners |  | 13/09 – Complete end-end reviews with all service owners on what evidence is required. |  | DG / CZ |  | 16/09 |  | In progress | 
29 |  | Identify audit resource |  | 13/09 – Agree who will be available for the audit dates and where required provide coaching for all teams. |  | DG / CZ |  | 30/09 |  | In progress | 
30 |  | Confirm new audit dates |  | 13/09 – Stage 1 (15th – 17th October), Stage 2 (Nov 11th / 12th) & (Dec 6th, 11th, 12th, 13th & 17th) |  | DG |  | 16/09 |  | Complete | 
31 |  | Revised any GAPS from the internal audit |  | 13/09 – Follow up with any gaps from the LQRA GAP analysis and internal audit. |  | DG / CZ |  | 15/10 |  | In progress | 
Key Issues and Challenges |  |  |  |  |  |  |  |  |  |  | 
# | Description | Description | Update |  |  | Type (RAID) | Type (RAID) | Type (Risk / Issue/ Defect) |  |  | Status
R1 | Resource |  | 04/07 – Stretch targets are being met, but contingency on approvals for control standards. |  |  | Risk | Risk |  |  |  | Open
R2 | Data Masking, Business continuity, disaster recovery and SIAM. |  | 04/07 – DG creating a control standard and agree mitigation for any BCP planning. |  |  | Risk | Risk |  |  |  | Open
R3 | ISO has to be operating 3 months before audit |  | 04/07 – Data sets and historical evidence available but requires alignment with measurement and analysis clause. |  |  | Risk | Risk |  |  |  | Open
R4 | Document volume |  | 04/07 – Management clauses in final draft, require completion of control standards. |  |  | Issue | Issue |  |  |  | Open
Key | Closed | In progress | Issue

## Slide 18
ISO27001 – Executive Summary
ISO27001 Flash Report |  |  |  |  |  |  |  |  |  |  | 
Programme Governance: |  | Denis Gallacher / Connor McCann |  |  | Budget Status: |  |  | Budget Status: | Unknown |  | 
Status Date: |  | 13/09/24 |  |  |  |  |  |  |  |  | 
Overall Status |  | Green |  |  |  |  |  |  |  |  | 
Target end date: |  | 31/12/24 |  |  |  |  |  |  |  |  | 
Programme Stage: |  | Delivery |  |  |  |  |  |  |  |  | 
Executive Summary |  | We have completed and internal audit, control gaps must be resolved. |  |  |  |  |  |  |  |  | 
Challenges / Concerns: |  | Resourcing and timelines |  |  |  |  |  |  |  |  | 
# |  | Action |  | Update | Owner | Owner |  | Due |  | Status | Status
15 |  | Review Quotes for Audit |  | 02/08 – Awaiting feedback from procurement. | DG / CM | DG / CM |  | 09/08 |  | In progress | In progress
18 |  | Complete mandatory control documentation & finalise performance |  | 02/08 – Awaiting completion of the 3rd party and data standards. Follow up discussion with Sean / Legal on 8th August. | DG / CM | DG / CM |  | 23/08 |  | In progress | In progress
20 |  | Training Plan and Develop Operating Procedures. |  | 02/08 – Majority of training is complete, but outstanding data and 3rd party standards to finalise operating procedures. | DG / CM | CM / CZ |  | 23/08 |  | In progress | In progress
21 |  | Setup governance forums & begin risk treatment reviews |  | 02/08 – Governance forums have been agreed, and some are in flight e.g. vulnerability management. Agreed to setup next week. | DG | DG / CM / SLT |  | 23/08 |  | In progress | In progress
22 |  | Initiate training with the Service Owners for: Risk / Information Security Management & Training |  | 02/08 – Outstanding dependency on 3rd party training. | DG / CM | CM / CZ |  | 23/08 |  | In progress | In progress
19 |  | SLT Review Management Clauses |  | 02/08 – Request SLT to review the management clauses and sign for approval. |  | SLT |  | 23/08 |  | In progress | 
25 |  | Audit framework |  | 02/08 – Greg has completed and audit framework, based on our controls. |  | GF/CM |  | 23/08 |  | Complete | 
26 |  | Information asset mapping |  | 02/08 – complete information asset mapping for our key systems e.g. PII etc. Affected by Data Standard. |  | CM/CZ |  | 23/08 |  | In progress | 
27 |  | SLT Training |  | 02/08 – Agenda under review, proposing to take place the week of 12th as we are awaiting data standard sign off |  | DG / CM / CZ |  | 23/08 |  | In progress | 
Key Issues and Challenges |  |  |  |  |  |  |  |  |  |  | 
# | Description | Description | Update |  |  | Type (RAID) | Type (RAID) | Type (Risk / Issue/ Defect) |  |  | Status
R1 | Resource |  | 04/07 – Stretch targets are being met, but contingency on approvals for control standards. |  |  | Risk | Risk |  |  |  | Open
R2 | Data Masking, Business continuity, disaster recovery and SIAM. |  | 04/07 – DG creating a control standard and agree mitigation for any BCP planning. |  |  | Risk | Risk |  |  |  | Open
R3 | ISO has to be operating 3 months before audit |  | 04/07 – Data sets and historical evidence available but requires alignment with measurement and analysis clause. |  |  | Risk | Risk |  |  |  | Open
R4 | Document volume |  | 04/07 – Management clauses in final draft, require completion of control standards. |  |  | Issue | Issue |  |  |  | Open
Key | Closed | In progress | Issue

## Slide 19
ISO27001 – Executive Summary
ISO27001 Flash Report |  |  |  |  |  |  |  |  |  |  | 
Programme Governance: |  | Denis Gallacher / Connor McCann |  |  | Budget Status: |  |  | Budget Status: | Unknown |  | 
Status Date: |  | 04/07/24 |  |  |  |  |  |  |  |  | 
Overall Status |  | Green |  |  |  |  |  |  |  |  | 
Target end date: |  | 31/12/24 |  |  |  |  |  |  |  |  | 
Programme Stage: |  | Initiation and Planning (Chase for training completion) |  |  |  |  |  |  |  |  | 
Executive Summary |  | We have partially completed most activities, apart from all control standards. This is due to resourcing, response times and challenges with A/L. Management clauses nearing completion. Requesting Sept 24 extension. |  |  |  |  |  |  |  |  | 
Challenges / Concerns: |  | Resourcing and timelines |  |  |  |  |  |  |  |  | 
# |  | Action |  | Update | Owner | Owner |  | Due |  | Status | Status
15 |  | Review Quotes for Audit |  | 04/07 – Coordinate with the business for a ‘group’ deal. LRQA have quoted 16,775K. Budget 20K for audit. Meeting Monday. | DG / CM | DG / CM |  | 10/06 |  | In progress | In progress
16 |  | Document ISMS – 6 clauses, including leadership, strategy, comms, objectives, management buy in and all inputs and outputs. |  | 04/07 – Final modifications, all documents are in final draft and will be published by the 5th July on the SharePoint. | DG / CM | DG / CM |  | 21/06 |  | Complete | In progress
17 |  | Modify and agree final documentation with Trustwave for Management Clauses and Controls. |  | 04/07 – All management clauses are in final draft. Majority of control standards are complete, awaiting approval from various parties. | CM / CZ | CM / CZ / DG |  | 21/06 |  | Complete | Closed
18 |  | Complete mandatory control documentation & finalise performance |  | 04/07 – Awaiting approval for control documentation, there are few outstanding mandatory documents; DR Standard, Security Operating Procedures | DG / CM | DG / CM |  | 15/07 |  | In progress | In progress
20 |  | Training Plan and Develop Operating Procedures. |  | 04/07 – Training plan complete, subject to control approvals. Operating procedures are a WIP. | DG / CM | CM / CZ |  | 15/07 |  | In progress | In progress
21 |  | Setup governance forums & begin risk treatment reviews |  | 04/07 – Reviewed framework with Trustwave and SLT. This has now been approved. Agree start date for Governance Forums and Infosec to provide top 10 risks for the SLT to review. | DG | DG / CM / SLT |  | 15/07 |  | In progress | In progress
22 |  | Initiate training with the Service Owners for: Risk / Information Security Management & Training |  | 04/07 – Dependency on completion of the Annex A Control documentation. | DG / CM | CM / CZ |  | 15/07 |  | In progress | In progress
23 |  | Evidence gathering for the external audit & resolve control GAPS. |  | 04/07 – GF is currently creating a standard and has created ‘guidelines’ for what good looks like. We are planning on completing the audit / SOP approach by the 20th July. |  | DG / CM / CZ / GF |  | 20/07 |  | Complete | In progress
19 |  | SLT Review Management Clauses |  | 04/07 – Request SLT begin to review the management clauses and sign for approval. |  | SLT |  | 29/07 |  | In progress | 
24 |  | Perform final review with Trustwave |  | 04/7 – Trustwave have reviewed all management clauses but have recommended an on-site at Cannock to review and ensure audit preparedness. | DG / CM | DG / CM |  | 29/07 |  | Complete | In progress
Key Issues and Challenges |  |  |  |  |  |  |  |  |  |  | 
# | Description | Description | Update |  |  | Type (RAID) | Type (RAID) | Type (Risk / Issue/ Defect) |  |  | Status
R1 | Resource |  | 04/07 – Stretch targets are being met, but contingency on approvals for control standards. |  |  | Risk | Risk |  |  |  | Open
R2 | Data Masking, Business continuity, disaster recovery and SIAM. |  | 04/07 – DG creating a control standard and agree mitigation for any BCP planning. |  |  | Risk | Risk |  |  |  | Open
R3 | ISO has to be operating 3 months before audit |  | 04/07 – Data sets and historical evidence available but requires alignment with measurement and analysis clause. |  |  | Risk | Risk |  |  |  | Open
R4 | Document volume |  | 04/07 – Management clauses in final draft, require completion of control standards. |  |  | Issue | Issue |  |  |  | Open
Key | Closed | In progress | Issue

## Slide 20
ISO27001 – Executive Summary
ISO27001 Flash Report |  |  |  |  |  |  |  |  |  |  | 
Programme Governance: |  | Denis Gallacher / Connor McCann |  |  |  | Budget Status: |  | Budget Status: | Unknown |  | 
Status Date: |  | 02/05/24 |  |  |  |  |  |  |  |  | 
Overall Status |  | Green |  |  |  |  |  |  |  |  | 
Target end date: |  | 31/12/24 |  |  |  |  |  |  |  |  | 
Programme Stage: |  | Initiation and Planning |  |  |  |  |  |  |  |  | 
Executive Summary |  | We are moving forward with the initial GAP Analysis on Monday 8th April, allowing for refinement of the milestone 2 objectives. |  |  |  |  |  |  |  |  | 
Challenges / Concerns: |  | Resourcing and timelines |  |  |  |  |  |  |  |  | 
# |  | Action |  | Update | Owner | Owner | Owner | Due |  | Status | Status
5 |  | Review go to market supplier strategy for ISO27001 audit in Q3 |  | 03/05 – Sue is now supporting to resolve and complete this action. | DG / CM | DG / CM | DG / CM | 12/04 |  | Closed | In progress
6 |  | Document ISMS – 6 clauses, including leadership, strategy, comms, objectives, management buy in and all inputs and outputs. |  | 03/05 – Extended timelines as we need to review all documentation for a pre-audit with Trustwave. | DG / CM | DG / CM | DG / CM | 31/05 |  | In progress | In progress
7 |  | Agree roles and responsibilities for ISO27001 |  | 03/05 – Document complete, ready for management review. | CM / CZ | CM / CZ | CM / CZ / DG | 12/04 |  | Closed | Closed
8 |  | Risk Management Framework and agree tooling |  | 03/05 – Risk Management framework draft complete, follow up with the SLT on approach. Docs to be released to the SLT | DG / CM | DG / CM | DG / CM | 12/04 |  | Closed | In progress
9 |  | GAP Analysis |  | 03/05 – Reviewed GAP analysis with Trustwave. | DG / CM | DG / CM | DG / CM | 12/04 |  | Closed | In progress
10 |  | Complete overall security information policy |  | 03/05 – Complete | CM / CZ | CM / CZ | CM / CZ | 18/04 |  | Closed | In progress
11 |  | Finalise project plan |  | 03/05 – Work in progress, extended timeline as focus has been on documentation. Document tracking in use for this. | DG | DG | DG | 31/05 |  | Closed | In progress
12 |  | Milestone 1 & 2 completion / Checklist |  | 03/05 – Document tracking in progress. | DG / CM | DG / CM | DG / CM | 18/04 |  | Closed | In progress
13 |  | Annex A Controls – Vulnerability Mgt |  | 03/05 – Vulnerability Management standard is nearly completed, and slight modification required. Moving to controls |  |  | CM / CZ | 01/05 |  | Closed | In progress
14 |  | ISO27001 SharePoint |  | 03/05 – Review with Graham Parkin to create an ISO27001 SharePoint for review. Expected to complete early May for audit and Management review. |  |  | DG / CM | 31/05 |  | Closed | In progress
Key Issues and Challenges |  |  |  |  |  |  |  |  |  |  | 
# | Description | Description | Update |  | Type (RAID) |  |  | Type (Risk / Issue/ Defect) |  |  | Status
R1 | Resource |  | 03/05 – We are scoping resource based on current requirements, this can change. Mitigating by high level resource plan. |  | Risk |  |  |  |  |  | Open
R2 | Data Masking, Business continuity, disaster recovery and SIAM. |  | 03/05 – Challenges with key controls, review as part of scoping and agree mitigation / risk treatment were applicable. |  | Risk |  |  |  |  |  | Open
R3 | ISO has to be operating 3 months before audit |  | 03/05 – Discussion with the trainer indicated as long as we are following the general controls this can be used as evidence. |  | Risk |  |  |  |  |  | Open
R4 | Document volume |  | 03/05 – Extension documentation is required for ISO, we are working as quickly as possible with a plan to meet the GAP review for mid April. |  | Issue |  |  |  |  |  | Open
Key | Closed | In progress | Issue

## Slide 21
ISO27001 – Executive Summary
ISO27001 Flash Report |  |  |  |  |  |  |  |  |  |  | 
Programme Governance: |  | Denis Gallacher / Connor McCann |  |  |  | Budget Status: |  | Budget Status: | Unknown |  | 
Status Date: |  | 07/03/24 |  |  |  |  |  |  |  |  | 
Overall Status |  | Green |  |  |  |  |  |  |  |  | 
Target end date: |  | 31/12/24 |  |  |  |  |  |  |  |  | 
Programme Stage: |  | Initiation and Planning |  |  |  |  |  |  |  |  | 
Executive Summary |  | We are moving forward with the initial GAP Analysis on Monday 8th April, allowing for refinement of the milestone 2 objectives. |  |  |  |  |  |  |  |  | 
Challenges / Concerns: |  | Resourcing and timelines |  |  |  |  |  |  |  |  | 
# |  | Action |  | Update | Owner | Owner | Owner | Due |  | Status | Status
5 |  | Review go to market supplier strategy for ISO27001 audit in Q3 |  | 03/05 – Sue is now supporting to resolve and complete this action. | DG / CM | DG / CM | DG / CM | 12/04 |  | Closed | In progress
6 |  | Document ISMS – 6 clauses, including leadership, strategy, comms, objectives, management buy in and all inputs and outputs. |  | 03/05 – Extended timelines as we need to review all documentation for a pre-audit with Trustwave. | DG / CM | DG / CM | DG / CM | 31/05 |  | In progress | In progress
7 |  | Agree roles and responsibilities for ISO27001 |  | 03/05 – Document complete, ready for management review. | CM / CZ | CM / CZ | CM / CZ / DG | 12/04 |  | Closed | Closed
8 |  | Risk Management Framework and agree tooling |  | 03/05 – Risk Management framework draft complete, follow up with the SLT on approach. Docs to be released to the SLT | DG / CM | DG / CM | DG / CM | 12/04 |  | Closed | In progress
9 |  | GAP Analysis |  | 03/05 – Reviewed GAP analysis with Trustwave. | DG / CM | DG / CM | DG / CM | 12/04 |  | Closed | In progress
10 |  | Complete overall security information policy |  | 03/05 – Complete | CM / CZ | CM / CZ | CM / CZ | 18/04 |  | Closed | In progress
11 |  | Finalise project plan |  | 03/05 – Work in progress, extended timeline as focus has been on documentation. Document tracking in use for this. | DG | DG | DG | 31/05 |  | In progress | In progress
12 |  | Milestone 1 & 2 completion / Checklist |  | 03/05 – Document tracking in progress. | DG / CM | DG / CM | DG / CM | 18/04 |  | Closed | In progress
13 |  | Annex A Controls – Vulnerability Mgt |  | 03/05 – Vulnerability Management standard is nearly completed and slight modification required. Moving to controls |  |  | CM / CZ | 01/05 |  | Closed | In progress
14 |  | ISO27001 SharePoint |  | 03/05 – Review with Graham Parkin to create an ISO27001 SharePoint for review. Expected to complete early May for audit and Management review. |  |  | DG / CM | 31/05 |  | In progress | In progress
Key Issues and Challenges |  |  |  |  |  |  |  |  |  |  | 
# | Description | Description | Update |  | Type (RAID) |  |  | Type (Risk / Issue/ Defect) |  |  | Status
R1 | Resource |  | 03/05 – We are scoping resource based on current requirements, this can change. Mitigating by high level resource plan. |  | Risk |  |  |  |  |  | Open
R2 | Data Masking, Business continuity, disaster recovery and SIAM. |  | 03/05 – Challenges with key controls, review as part of scoping and agree mitigation / risk treatment were applicable. |  | Risk |  |  |  |  |  | Open
R3 | ISO has to be operating 3 months before audit |  | 03/05 – Discussion with the trainer indicated as long as we are following the general controls this can be used as evidence. |  | Risk |  |  |  |  |  | Open
R4 | Document volume |  | 03/05 – Extension documentation is required for ISO, we are working as quickly as possible with a plan to meet the GAP review for mid April. |  | Issue |  |  |  |  |  | Open
Key | Closed | In progress | Issue

## Slide 22
ISO27001 – Executive Summary
ISO27001 Flash Report |  |  |  |  |  |  |  |  |  |  | 
Programme Governance: |  | Denis Gallacher / Connor McCann |  |  |  | Budget Status: |  | Budget Status: | Unknown | Green | 
Status Date: |  | 07/03/24 |  |  |  |  |  |  |  |  | 
Overall Status |  | Green |  |  |  |  |  |  |  |  | 
Target end date: |  | 31/12/24 |  |  |  |  |  |  |  |  | 
Programme Stage: |  | Initiation and Planning |  |  |  |  |  |  |  |  | 
Executive Summary |  | We are currently developing the scoping, risk and management control documentation as part of milestones 1 & 2. Management sign off will be required before moving to Milestone 3 plan - control implementation. |  |  |  |  |  |  |  |  | 
Challenges / Concerns: |  | Resourcing and timelines |  |  |  |  |  |  |  |  | 
# |  | Action |  | Update | Owner | Owner | Owner | Due |  | Status | Budget
1 |  | Arrange training for the team on ISO27001 |  | 07/24 – Training has now been arranged for all team members. | DG | DG | DG | 08/03 |  | Closed | 
2 |  | Review approach with Trust Wave and agree support |  | 07/24 – Meeting with Trustwave to understand best practice approach. | DG | DG | DG | 08/03 |  | Closed | 
3 |  | Policy and procedure review, approach and templates |  | 07/24 – Discussed with Claire / Connor on policy list, approach and template standard. All required policies are being updated and documented. Completion is applicable to Milestone 3. | DG / CM / CZ | DG / CM / CZ | DG / CM / CZ | 08/03 |  | Closed | 
4 |  | Reach out to Aggreko business to understand ISO standard accreditation's |  | 07/24 – Agreed to arrange a meeting with Ken / Dave from Aggreko H&SE to understand how they achieved ISO9001, 45001, 50001.Meeting on 11th March 2024. | DG | DG | DG | 08/03 |  | Closed | 
5 |  | Review go to market supplier strategy for ISO27001 audit in Q3 |  | 07/24 – Work with procurement to find an appropriate Auditors and select preferred partner. | DG / CM | DG / CM | DG / CM | 31/03 |  | In progress | 
6 |  | Document ISMS – 6 clauses, including leadership, strategy, comms, objectives, management buy in and all inputs and outputs. |  | 07/24 – Complete for review by 31st March 2024. Agree management meeting for sign off | DG / CM | DG / CM | DG / CM | 31/03 |  | In progress | 
7 |  | Agree roles and responsibilities for ISO27001 |  | 07/24 – Work in progress, Claire has started detailing roles and will apply to ISMS. | CM / CZ | CM / CZ | CM / CZ | 31/03 |  | In progress | 
8 |  | Risk Management Framework and agree tooling |  | 07/24 – Present the risk management framework to SLT. It is a requirement of ISO to commit to reviews, but we want a consolidated risk review mechanism. | DG / CM | DG / CM | DG / CM | 31/03 |  | In progress | 
9 |  | GAP Analysis |  | 07/24 – Complete scoping documentation and risk review, we will conduct a GAP Analysis with Trustwave to finalise our approach on tech / management controls and complete a pre-audit. | DG / CM | DG / CM | DG / CM | 12/04 |  | In progress | 
10 |  | Complete overall security information policy |  | 07/24 – Focus on the primary and overarching Information security policy. CM reworking. | CM / CZ | CM / CZ | CM / CZ | 18/04 |  | In progress | 
11 |  | Finalise project plan |  | 07/24 – Revise and finalise the current project plan with the goal to deliver an early-stage audit by Q3 2024. | DG | DG | DG | 18/04 |  | In progress | 
12 |  | Milestone 1 & 2 completion / Checklist |  | 07/24 – Agree that all actions from Milestone 1 and 2 are complete, engage Trustwave for final review of all actions to close. | DG / CM | DG / CM | DG / CM | 18/04 |  | In progress | 
13 |  | Annex A Controls – Vulnerability Mgt |  | 07/24 – Vulnerability Management standard is nearly completed and expected to be issued next week. |  |  | CM / CZ | 01/05 |  | In progress | 
Key Issues and Challenges |  |  |  |  |  |  |  |  |  |  | 
# | Description | Description | Update |  | Type (RAID) |  |  | Type (Risk / Issue/ Defect) |  |  | Status
R1 | Resource |  | 07/24 – We are scoping resource based on current requirements, this can change. Mitigating by high level resource plan. |  | Risk |  |  |  |  |  | 
R2 | Data Masking, Business continuity, disaster recovery and SIAM. |  | 07/24 – Challenges with key controls, review as part of scoping and agree mitigation / risk treatment were applicable. |  | Risk |  |  |  |  |  | 
Key | Closed | In progress | Issue

## Slide 23
Roles and Responsibilities
Role | Description | RACI
Project Manager | Responsible for overall project management, including governance. Include agreeing final scope with the teams, consulting, training. Supports creating templates / supporting control reviews to meet audit standards. Arrange internal / external audit. | Accountable for project delivery and advising on any challenges, risks, issues and dependencies that could impact delivery. Supports consultation and informing.
Security | Ensures controls and standards are fit for purpose as part of the overall ISO27001 framework. Identifies clear scope and creates policies / procedures within the security remit. Checks that all theme’s, policies and controls are met under the standard. | Account and Responsible for ensuing and agreeing that our ISMS system meets standards, and all controls are documented and are FIT for purpose. Supports consultation and informing.
Infrastructure | Supports enforcing controls and ensuring these can be met. | Accountable, Informed and Consulted on the implementation of control, standards and meeting auditing requirements.
Service Owners | Supports enforcing controls and ensuring these can be met. | Accountable, Informed and Consulted on the implementation of control, standards and meeting auditing requirements.
Service Management | Supporting controls in relation to ITSM processes, including change, asset management, IAM and any CSI requirements. | Accountable, Informed and Consulted on the implementation of control, standards and meeting auditing requirements.

## Slide 24
ISMS and Roles & Responsibility Mapping
Maintain & Improve: CSI, Corrective Actions and Non-Conformance
Activities
Conduct periodic assessment audits.
Continuous Improvement.
Implement corrective and preventative actions.
Roles & Responsibilities
Information / Operational Security – Develop plans with Service Owners
ATS Leadership – Provide resources for CSI and remediation.
Service Owners – Implement corrective / preventative actions.
Establish: Set Policies, Context, Issues and Objectives
Activities
Identify business objectives, obtain management support, GAPS & scope.
Create project plan, context, planning and support clauses.
Review & validate organisational security / document controls / procedures.
Statement of applicability and ID risks / establish risk appetite.
Roles & Responsibilities
Information Security – Create clauses, risk approach, policies & controls.
ATS Leadership Team – Approve ISO27001 Policies and Clauses e.g. Leadership & Commitment / Information Security Policy / Agree risk appetite.
Service Owners – Review policies, procedures & controls.
Monitor: Management Reviews, Performance & Internal Audit
Activities
Evaluation, Monitor and assess ISMS performance.
Management meeting reviews.
Audits and logging.
Roles & Responsibilities
Information / Operational Security – Performance evaluations, control assurance and provide management reporting.
ATS Leadership – Review evaluation reports.
Service Owners – Evaluate internal auditing and external auditing and report conformance issues e.g. SOC Reports.
Implement: Operational Control Execution, Risks, Support
Activities
Service adopt security measures / implement governance & reporting.
Manage the risks and create a risk treatment plan.
Implement policies, procedures, controls and treat risks.
Allocate resources and train staff.
Roles & Responsibilities
Information / Ops security – Support control implementation / Governance & training.
ATS Leadership – Begin risk reviews, with meeting minutes.
Service Owners – Report risks / nonconformities and follow security measures.
Group Functions – HR / L&D support training
Note: We are still establishing the ISMS and requesting consultancy / feedback from Trustwave, and therefore this is subject to change.
Plan
Do
Check
Act
Security &
Policy objectives
Risk assessment & control
Implement risk treatment plans
Monitor & Review ISMS
Maintain & improve
ISMS

## Slide 25
ISMS – Risk Framework
The factors which influence how we manage information security at Aggreko.
Internal:
Governance & structure, culture, values, resources, processes, the data we hold, the existing security management system.
External:
Industry & market conditions, legal and regulatory requirements, external stakeholders, Threat Environment
Understanding our assets, what our vulnerabilities are, and what could negatively impact our assets.
Asset management (data, apps, systems, infra),
Characteristics (sensitivity, criticality, dependency, value), vulnerabilities (systems, processes or controls, technical and non-technical)
Threats: source - who or what could compromise your known or unknown assets e.g cyber attack, physical, insider, natural disaster (Dubai is a good example)
Type – ransomware, unauthorized access, cloud misconfiguration, physical damage.
Assessing the identified vulnerability & known threats to gauge potential impacts and likelihoods of the risk materialising.
Risk severity to be classified (Low, medium, high, severe) based on the ATS risk appetite (yet to be agreed and approved). Each severity classification - like incidents - will have associated processes and escalations. E.g. A Severe risk, such as a 10/10 external vulnerability is affecting our firewalls and attempted exploits are imminent would be flagged immediately to relevant senior management. A minor bug in an application would not.
Maintaining quality, consistent documentation of the risk assessment and treatment process, including auditable records of plans and outcomes.
Determining if we should tolerate the identified risk or not.
We will track three risk ratings for each risk:
Inherent Risk - the level or raw or untreated risk before any control application or mitigation.
Residual risk - the level or risk present after treatment has been applied which mitigates some or all risk.
Target Risk - the level of risk that is satisfactory after new mitigation measures have been introduced.
Treating the residual risk until it sits within risk appetite for Aggreko, ATS and the risk owner.
Residual risk can be treated by taking any of the following actions:
Modification – Add, remove or alter controls.
Retention – Accept the current risk level
Avoidance – Stop or change what is causing the risk
Sharing – outsource or get insurance
Retention would be chosen in 2 scenarios:
The risk is low and mitigation is not cost effective.
Business opportunity outweighs the risk.